# PipeFrame Simulation Workbench Project Plan

Proposed software engineering project

| Student | Doan Minh Hieu Vo | CSU ID | 2906508 |
| --- | --- | --- | --- |
| Sponsor | Doan Si Sang Vo | Sponsor role | Mechanical engineering adviser |
| Duration | 16 weeks | Plan date | September 11, 2026 |

# Project Description

PipeFrame will be a reusable simulation engine and visual workbench for creating, running, and analyzing interactive two-dimensional simulations. The project will separate reusable services—such as rendering, physics, spatial queries, simulation time, assets, telemetry, and editor tools—from the rules of any one simulation. Developers will use common engine interfaces while project code defines domain behavior.

Three reference applications will demonstrate the design. An ant colony will test large populations, spatial indexing, collisions, and environmental fields. A sailboat simulation will test vehicle physics, wind, water, navigation, instrumentation, and time-dependent behavior. A modular robotics simulation will let users assemble robots from individual parts, connect them, write control logic, and test autonomous behavior in editable environments.

# Need and Purpose

Small simulation projects often duplicate their windowing, rendering, input, physics, timing, debug, and user-interface code. They also become tightly coupled to a graphics library, making reuse and extension difficult. PipeFrame will provide a stable, backend-neutral foundation and an editor that exposes scene objects, transforms, components, assets, connections, and runtime data through consistent workflows.

The robotics application will show why this separation matters. It will support configurable chassis, wheels, motors, batteries, controllers, ultrasonic sensors, LiDAR, infrared sensors, servos, LEDs, and other compatible parts. An ELEGOO UNO R3 Smart Robot Car style assembly will serve as an initial reference, but the system will support different kits and custom robots.

# Project Objectives

• Design reusable engine interfaces that keep application code independent of SFML and other backend details.

• Provide deterministic simulation timing, physics, spatial queries, rendering, resources, input, debugging, and telemetry.

• Create a visual editor for scene construction, object hierarchy, component properties, assets, reusable assemblies, undo and redo, and simulation control.

• Allow projects to register new components, inspector fields, tools, overlays, assets, and panels without modifying the editor.

• Demonstrate reuse through ant colony, sailboat, and modular robotics applications.

• Validate behavior with automated tests, repeatable scenarios, performance measurements, and visual review.

# Planned Reference Applications

| Application | Primary purpose | Capabilities demonstrated |
| --- | --- | --- |
| Ant colony | Large-agent simulation | Spatial grids, collisions, fields, agent behavior, profiling, and interactive controls |
| Sailboat | Physics and learning | Wind and water response, navigation, simulation time, telemetry, training, and model inspection |
| Modular robotics | Assembly and autonomy | Parts, attachments, signals, sensors, actuators, environments, control logic, and autonomous navigation |

# Scope and Deliverables

• A reusable C++ engine library with backend-neutral public types and documented extension interfaces.

• A desktop simulation workbench with a viewport, hierarchy, inspector, asset browser, reusable assemblies, layouts, simulation controls, and diagnostic tools.

• Reusable systems for deterministic time, jobs, spatial indexing, physics, rendering, textures, audio, learning experiments, serialization, and replay.

• Three working reference applications with project-specific logic built on shared PipeFrame services.

• A modular robot builder supporting mechanical attachments, power and signal connections, configurable parts, sensor visualization, actuator control, and reusable robot designs.

• Editable test environments containing walls, obstacles, tracks, targets, spawn points, and navigation challenges.

• Automated tests, validation scenarios, performance measurements, user documentation, and project demonstrations.

# Proposed Schedule

| Weeks | Phase | Planned work | Review |
| --- | --- | --- | --- |
| 1–2 | Requirements and architecture | Confirm scope, boundaries, units, data formats, reference behavior, and acceptance criteria. | Plan |
| 3–4 | Core runtime | Build deterministic timing, backend interfaces, resources, serialization, logging, and tests. | Demo |
| 5–6 | Physics and spatial systems | Implement bodies, collisions, spatial grids, environmental fields, and debug views. | Test |
| 7–8 | Editor foundation | Create viewport tools, hierarchy, inspector, undo and redo, assets, and extension APIs. | Demo |
| 9–10 | Ant application | Implement colony behavior, food and pheromones, interaction, metrics, and validation. | Review |
| 11–12 | Sailboat application | Implement vehicle behavior, navigation, telemetry, training, and reference comparison. | Review |
| 13–14 | Modular robotics | Add parts, connections, drivetrain, ultrasonic and LiDAR sensing, LEDs, and controllers. | Demo |
| 15–16 | Integration and delivery | Build autonomy examples; finish tests, documentation, performance review, and presentation. | Final |

# Roles and Responsibilities

Student developer. I will design and implement the engine, editor, reference applications, tests, documentation, and demonstrations.

Project sponsor. Doan Si Sang Vo will provide mechanical engineering guidance, review robot assemblies and motion assumptions, and evaluate whether the editor supports practical component placement and configuration.

# Risks and Scope Control

• The feature set is larger than a typical academic term. Work will be delivered in usable slices, and advanced features will be deferred if core workflows are unstable.

• Exact fluid, electrical, and sensor behavior may be too costly to reproduce. Each model will state its fidelity, assumptions, limits, and validation targets.

• Editor complexity and heavy simulation loads may slow progress. Shared acceptance tests, profiling, and adjustable fidelity will guide scope and optimization.

# Success Criteria

The project will be successful when all three reference applications run through common PipeFrame services; project-facing code does not depend directly on SFML; scenes and settings save and reload correctly; editor operations support undo and redo; simulations can be paused, stepped, reset, and replayed; and automated tests verify deterministic behavior and core workflows. For robotics, users must be able to assemble at least two different robots from compatible parts, create an environment, connect sensors and actuators, provide control logic, inspect telemetry, and complete an obstacle-avoidance or navigation task without changing the editor source.